## Gantt
CIT498-01 Final Project | [5 empty] | Legend:
Austin Herb | [5 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
BASELINE GANTT CHART |  | Project Start Date: |  | 2019-05-15
|  | Display Week: |  | 1 |  | May | [20 empty] | June | [27 empty] | July | [30 empty] | August
 | time axis 2019-05-13 to 2019-08-11
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13
Milestone Description | Category | Assigned To | Progress | Start | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Pre-Development Phase
Identify website features | On Track | Austin Herb | 100% | 2019-05-15 | 7
Develop project proposal | On Track | Austin Herb | 100% | 2019-05-21 | 5
Develop project proposal presentation | On Track | Austin Herb | 100% | 2019-05-26 | 3
Replace Lorem Ipsum text | Low Risk | Austin Herb | 100% | 2019-05-26 | 2
Present project proposal | On Track | Austin Herb | 100% | 2019-05-29 | 1
Develop Gantt chart | On Track | Austin Herb | 100% | 2019-05-30 | 5
Feature Development Phase
Implement user login system | Low Risk | Austin Herb | 100% | 2019-06-03 | 7
Create end user documentation for user login system | Low Risk | Austin Herb | 100% | 2019-06-08 | 2
Implement contact us notification system | On Track | Austin Herb | 100% | 2019-06-10 | 7
Create end user documentation for contact us notification system | Low Risk | Austin Herb | 100% | 2019-06-15 | 2
Take employee photos | Low Risk | Austin Herb | 0% | 2019-06-14 | 1
Events/alerts calendar research | Med Risk | Austin Herb | 100% | 2019-06-17 | 7
Implement events/alerts calendar and notification system | High Risk | Austin Herb | 85% | 2019-06-17 | 14
Create end user documentation for events/alerts calendar notification system | Low Risk | Austin Herb | 85% | 2019-06-27 | 4
maintenance request research | Med Risk | Austin Herb | 100% | 2019-07-01 | 7
Implement maintenance request notification system | High Risk | Austin Herb | 100% | 2019-07-01 | 14
Create end user documentation for maintenance request notification system | Low Risk | Austin Herb | 100% | 2019-07-11 | 4
SMS notification research | Med Risk | Austin Herb | 100% | 2019-07-15 | 7
Implement SMS notification system | Med Risk | Austin Herb | 100% | 2019-07-15 | 14
Create end user documentation for SMS notification system | Low Risk | Austin Herb | 100% | 2019-07-25 | 4
Implement the existing RentManager system | Low Risk | Austin Herb | 100% | 2019-07-29 | 1
Post-Development Phase
Bug fixes | Med Risk | Austin Herb | 75% | 2019-07-30 | 7
Final site launch | Low Risk | Austin Herb | 100% | 2019-08-06 | 1
Final site presentations | Low Risk | Austin Herb | 0% | 2019-08-06 | 3
To add more data, Insert new rows ABOVE this one

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. Change the display week number to change the timeline view. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with input messages. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. To remove these instructions from the worksheet, go to Data > Data Tools > Data Validation > Input Message and delete them.
This is the last instruction in this worksheet.